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Demolition Process Document
The demolition process consists of a number of steps; Demo Permit (Town Jurisdiction Only), Utility Disconnects, Asbestos Inspection – Report, Abatement (If Applicable), and Structure/Organics removal: 
· MCH – Request Demo Proposal from Scott Hitchens.  This proposal is to include the fee for the asbestos inspection, silt fence, and temp drive. Notify Scott if the client is using Second Chance.  
· MCH – Request Plumbing Disconnect Proposal from MDP Plumbing. This proposal is to include the disconnect for the water and sewer.  Please note that it is common for MDP to include a fee for upgrading the existing sewer service to the current code requirement. 
· MCH – Coordinate Second Chance schedule if applicable. 
· Request from Client - Billing Name Preference & Address 
· Request from Client - Move Out Date 
· Request from Client - Requests for protecting/keeping trees or items from the house? Flag items on site prior to demo and confirm with the demo contractor. 
· Request from Client - Delmarva Power Account Number: MCH to submit a Demo application, but DPL also requires the client to contact Customer Service to approve the meter termination. Client to contact DPL at (1-800-375-7117) or https://secure.delmarva.com/CustomerServices/service/landing to finalize disconnect request.
· Notify Client - Media Provider: Client to contact their media provider to discontinue service at the applicable move out date.  The client will need to return leased equipment.
· Request from Client - Water - Sussex Shores, Artesian, Town (Bethany): Client to provide their account number.  MCH plumber will handle the disconnect process directly with the water company. (Proposal for this service will be sent for approval).
· Notify Client - Sussex County Sewer: MCH plumber will obtain the applicable permit and inspection to disconnect the sewer.  (Proposal for this service will be sent for approval).
· Request from Client - Gas Service: Client to contact their provider, if applicable, to disconnect the gas service and remove any tanks.  If metered service, the client will need to let the provider know that the existing house will be torn down.
· Notify Client - Asbestos Inspection (3rd Party): Please provide access for this inspection.  This inspection can take place at any time and is non-invasive.  If asbestos is detected, an abatement proposal will be formulated.  The cost for the inspection will be included in the demolition proposal, and will be sent for approval.  Ideally, this is scheduled at least a month prior to the expected demo date to account for abatement if applicable. 
· MCH - Demo Permit needed for Fenwick Island (Mike Locke), South Bethany (Joe Hinks), & Bethany Beach (Susan Frederick).  Applications saved in MCH Process Documents – Permit Docs/Applications.  The application, demo & plumbing disconnect proposals, asbestos report, and site plan are required for submission.  The town reviewer will follow up with a cost which will be relayed to Jon Subity to cut a check. 
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